## Sheet1
Activity | Symbol | Tracking Unit | Comments
Access Roads Rough Grade (ready for const traffic) |  | LF
Access Roads Finish Graded & Graveled |  | LF
Upgrade Existing Roads (ready for const traffic) |  | LF
Upgrade Existing Roads Finish Graded & Graveled |  | LF
WTG Foundations
Excavated |  | EA
Rebar Installed |  | EA
Concrete Poured |  | EA
Backfilled & Compacted |  | EA
WTG Padmount Transformer (PMT) & Low Voltage Work
WTG PMT Set |  | EA
UG Electrical Collection System Cable Installed |  | LF
Feeder A |  | EA
Feeder B |  | EA
Feeder C |  | EA
Feeder D |  | EA
Feeder E |  | EA
Feeder F |  | EA
Feeder G |  | EA
Feeder H |  | EA
Feeder I |  | EA
Feeder J |  | EA
Feeder K |  | EA
Feeder L |  | EA
Feeder M |  | EA
Feeder Energized |  | LF
Utility Interconnect Switchyard
Site Work |  | LS
Foundations |  | LS
Equipment Set/Terminations Complete |  | LS
Energize |  | LS
Project Substation 34.5/345kV/334MVA
Site Work |  | LS
Foundations |  | LS
MPT Delivered/Dressed Out |  | LS
Equipment Set/Terminations Complete |  | LS
Energize |  | LS
345kV Overhead Transmission Line
ROW Cleared |  | LF
Frame Set Poles |  | LF
Sting/Sag/Clip Conductor |  | LF
Energize |  | LF
O&M Building
Site Work |  | LS
Building Exterior Complete |  | LS
Building Interior Complete |  | LS
Building Complete/Owner Turnover |  | LS
O&M Building Warehouse
Site Work |  | LS
Building Exterior Complete |  | LS
Building Interior Complete |  | LS
Building Complete/Owner Turnover |  | LS
WTG Installation
Offload WTG Components |  | LS | LS progress when all components deliveried
Base / Mid |  | LS | LS progress when based/mid stacked out
Tops / Nacelles / Rotor Erection |  | LS | LS progress when all components deliveried
WTG Electrically Complete |  | EA
WTG Mechanical Completion |  | EA
Pre-Commissioning |  | EA
Full Commissioning |  | EA
Schedule Drop Down Embedded At WTG Location on Map
Schedule Finish Date | 2016-05-16
Actual Finish Date | 2016-04-16
Variance | -30

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only