## Master Projects (1)
Construction Bid Package | Description | FY | Construction Start Date | Material Status | Comments | EditDate | Design Status | Design Status Notes | Borrow Site Dedicated | Borrow Site Dedicated Name | Berm Material Type | Berm Material Quantity | Levee Material Type | Levee Material Quantity | Rip Rap Material Type | Rip Rap Quantity
Natomas Reach C |  | 2020 |  |  |  | 4/23/2020, 1:54 PM
NLIP Window Highway 99 |  |  |  |  | To Be Constructioned By the Corps | 4/28/2020, 12:42 PM
WRDA 2016 ARN | Arcadia River | 2020 |  |  |  | 4/14/2020, 11:02 AM
NLIP Window Elkhorn Pumping Plant | Adjacent Levee w/Seepage Cutoff Wall and Seepage Berm |  |  |  |  | 4/28/2020, 12:16 PM |  |  | Unknown |  |  |  |  | -
NLIP Window Pritchard Lake/ Pumping Plant 2 | [5 empty] | 4/28/2020, 12:17 PM
Natomas Reach D |  |  |  |  | Sr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/23/2020, 1:59 PM
Natomas Reach B | Adjacent Levee w/Seepage Cutoff Wall and Seepage Berm | 2020 | 2020-04-14 | Shortage | I-5 Window at 65%, borrow material to come from I-5 site. NEED TO CONFIRMSr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:07 PM | 100% |  | Unknown | Cache Creek | per design | 100000 | "type 1" | 381900
Natomas Reach D | Pipeline Replacement, Drainage Canal Relocation, and Seepage Cutoff Wall Windows Closure | 2020 |  |  | Sr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:40 PM
Natomas Reach D | Pipeline Replacement, Drainage Canal Relocation, and Seepage Cutoff Wall Windows Closure | 2020 |  |  | Sr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:41 PM | 100%
Natomas Reach D | Window, unknown | 2020 |  |  | Sr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:39 PM
Natomas Reach D | Pipeline Replacement, Drainage Canal Relocation, and Seepage Cutoff Wall Windows Closure | 2020 |  | Shortage | Sr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:19 PM | 90% |  | Unknown
Natomas Reach B | Adjacent Levee w/Seepage Cutoff Wall and Seepage Berm | 2020 | 2020-04-14 | Shortage | I-5 Window at 65%, borrow material to come from I-5 site. NEED TO CONFIRMSr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:58 PM | 100% |  | Unknown | Cache Creek |  |  | "type 1" | 381900
Natomas Reach B | Adjacent Levee w/Seepage Cutoff Wall and Seepage Berm | 2020 |  |  | I-5 Window at 65%, borrow material to come from I-5 site. NEED TO CONFIRMSr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:36 PM |  |  | Unknown |  |  |  |  | 381900
Natomas Reach B | Adjacent Levee w/Seepage Cutoff Wall and Seepage Berm | 2020 | 2020-04-14 |  | Sr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:06 PM | 100% |  | Yes | Cache Creek |  |  | "type 1" | 381900
Natomas Reach B | Adjacent Levee w/Seepage Cutoff Wall and Seepage Berm | 2020 | 2020-04-14 |  | I-5 Window at 65%, borrow material to come from I-5 site. NEED TO CONFIRMSr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:08 PM | 100% |  | Unknown | Cache Creek |  | 381900 | "type 1" | 381900
Natomas Reach H | Seepage Cutoff Wall and Landside Levee Slope Improvements | 2020 |  | Shortage |  | 4/28/2020, 12:13 PM | 100% |  | Unknown |  |  | 95000 |  | 125500
Natomas Reach D | Pipeline Replacement, Drainage Canal Relocation, and Seepage Cutoff Wall | 2020 |  |  | Previously Constructed By Non-Federal Sponsors | 4/28/2020, 12:38 PM | 100%
Natomas Reach E | Seepage Cutoff Wall and Levee Slope Improvements | 2021 |  | Shortage |  | 4/28/2020, 12:11 PM | 30% | 65% due 8/1/20 | Yes | Kaufman |  | 221000 |  | 242500
LAR Subreach 1 |  | 2021 |  | Surplus | material estimate based on 60% designs | 4/28/2020, 12:26 PM | 60% |  | Yes | Arden Pond | [5 empty] | 298400
LAR Subreach 2 |  | 2021 |  | Shortage | material estimate based on 30% designs | 4/28/2020, 12:26 PM | 30% |  | Unknown | [6 empty] | 200000
SAC Weir |  | 2021 | 2020-04-01 | Shortage |  | 4/15/2020, 1:19 PM | 60%
I5 Window |  | 2021 |  | Shortage | I-5 Window at 65%, borrow material to come from I-5 site. NEED TO CONFIRMSr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:16 PM | 30% |  | Yes | from site, to confirm |  | 35000 |  | 25000
Natomas Reach C | NLIP Window Pritchard Lake/ Pumping Plant 2 | 2022 |  | Shortage |  | 4/28/2020, 12:09 PM | 0% |  | No |  |  | 80000 |  | 136500
LAR Subreach 3 |  | 2022 |  | Shortage | material estimate based on 30% designs | 4/28/2020, 12:26 PM | 30% |  | No | Approved Quarry | [5 empty] | 155000
Natomas Reach F | Seepage Cutoff Wall and Levee Slope Improvements | 2022 | 2021-03-31 | Unknown | To Be Constructioned By the Corps. Request 35% designs mid-Dec, begin initial take offs and revise as designs mature. | 4/28/2020, 12:11 PM | 30% |  | No
Natomas Reach I_Contract 2 | Contract 1: Levee Centerline Seepage Cutoff Wall - FY 19 & FY 20 Contract 2: Landside Levee Slope Improvements - FY 22 | 2022 |  | Shortage | In ConstructionSr. PM: John Hoge 916-557-5304john.a.hoge@usace.army.mil | 4/28/2020, 12:13 PM | 30% |  | Unknown |  |  |  |  | 44750
Natomas Reach G | Seepage Cutoff Wall and Levee Slope Improvements | 2022 | 2021-03-31 | Shortage |  | 4/28/2020, 12:12 PM | 30% |  | Unknown |  |  | 218000 |  | 250000
Folsom Dam Raise 1 |  | 2022 |  | Shortage | Pending Completion | 4/28/2020, 1:02 PM | 30% |  |  |  | 1000000 |  |  |  |  | 250000
Natomas Reach D | Pumping Plant 4 Replacement | 2022 |  | Unknown |  | 4/28/2020, 12:39 PM | 0% |  | Unknown
Folsom Dam Raise 2 |  | 2022-2023 |  | Shortage | Pending Completion | 4/28/2020, 1:04 PM | 30% |  | Unknown |  |  | 1200000 |  | 750000 |  | 75000
Natomas Reach A | Seepage Cutoff Wall & Levee Slope Improvements | 2022-2023 |  | Shortage | PM: John Powderly, 916-557-6887john.j.powderly@usace.army.mil | 4/28/2020, 12:06 PM | 0% |  |  | Cache Creek |  | 50000 |  | 120000
LAR Subreach 4 | Erosion | 2023 |  | Shortage | material estimate based on 30% designs | 4/28/2020, 12:26 PM | 30% |  | Yes | Approved Quarry | [5 empty] | 250000
Folsom Dam Raise 3 |  | 2023 |  | Shortage | Completed | 4/28/2020, 1:05 PM | 30% |  |  |  |  | 300000 |  | 250000 |  | 125500
South Sacramento River |  | 2023 |  | Unknown |  | 4/14/2020, 11:02 AM | 0%